HIVE

MVP Plan

Ship the smallest thing that proves the value proposition

8-Week Development Blueprint

Version 2.0 | March 2026 | ENRICHED EDITION

CONFIDENTIAL

# Executive Summary

The Hive MVP targets delivery of 36 P0 features in 8 weeks, executed by a two-person founding team. The plan follows a lean methodology: build the minimum viable product that demonstrates secure, observable AI agent orchestration with MCP-native communication.

MVP Philosophy "Ship the smallest thing that proves the value proposition." The MVP must answer one question: Can Hive make managing multiple AI agents significantly easier and safer than the current alternatives? Every feature included must directly contribute to answering YES.

| 36 P0 Features | 8 Weeks | 2 Founders | €3,520 Annual Infra |
| --- | --- | --- | --- |

# MVP Scope

The MVP includes 36 P0 features spanning 9 of 11 feature categories. Two categories (Storage advanced features and Admin advanced features) are deferred to Phase 2.

| Category | MVP Features | Key Deliverables |
| --- | --- | --- |
| Agent Lifecycle | 5 | Create, start, stop, delete, restart, health checks |
| Orchestration | 4 | Container provisioning, resource allocation, networking, runtime selection |
| Communication | 4 | MCP relay, Redis pub/sub, request/response, communication logging |
| Monitoring | 3 | Metrics dashboard, log aggregation, health status board |
| Security | 5 | JWT auth, RBAC, container isolation, secrets, audit logs, tool auth |
| Model Management | 2 | Multi-provider support, local model support (Ollama) |
| Networking | 2 | Service discovery (CoreDNS), reverse proxy (Traefik) |
| API & CLI | 3 | REST API, CLI tool, API rate limiting |
| UI Dashboard | 4 | Agent dashboard, detail view, metrics charts, creation form |
| Admin | 2 | User management, system settings |

# Team & Responsibilities

The MVP is built by a two-person founding team with complementary skills:

| Role | Allocation | Responsibilities | Key Skills |
| --- | --- | --- | --- |
| Founder 1 | Full-time | Full-stack development, AI integration, product design, UX, API design, frontend, agent lifecycle, MCP integration | Next.js, React, TypeScript, Python, Docker, AI/ML, Product Management |
| Founder 2 | Part-time | Infrastructure, security, DevOps, container orchestration, networking, database design, CI/CD | Linux, Docker, Firecracker, Networking, PostgreSQL, Security, Terraform |

Capacity Planning Founder 1: 40 hrs/week × 8 weeks = 320 hours. Founder 2: 20 hrs/week × 8 weeks = 160 hours. Total: 480 person-hours. With 25% buffer for bugs and unknowns, effective capacity is 360 hours.

# 8-Week Sprint Plan

Week 1-2: Foundation Project Setup, Auth, DB Schema, Docker Integration

## Goals

- Initialize Next.js 15 project with TypeScript, Tailwind, shadcn/ui

- Implement PostgreSQL schema with Drizzle ORM (10 core tables)

- Build JWT authentication with refresh tokens

- Set up Docker SDK integration for container management

- Configure Traefik reverse proxy with auto-TLS

- Implement CoreDNS for service discovery

## Deliverables

- Working Next.js app with auth flow

- Database with all core tables and migrations

- Docker API wrapper for container CRUD

- Traefik configuration with routing rules

- CoreDNS zone configuration for .hive.local

- CI/CD pipeline (GitHub Actions)

## Acceptance Criteria

- User can register, login, and refresh tokens

- Database migrations run cleanly on fresh install

- Docker containers can be created/started/stopped via API

- Traefik routes traffic to containers by name

- DNS resolves agent-name.hive.local correctly

Risks Docker SDK compatibility issues across OS versions ¦ Drizzle ORM learning curve may slow schema design

Week 3-4: Core Agent Management Create/Start/Stop/Delete Agents, Container Orchestration

## Goals

- Build agent creation wizard (template → config → deploy)

- Implement full agent lifecycle (create, start, stop, restart, delete)

- Configure container resource limits (CPU, memory, GPU)

- Build health check system with auto-recovery

- Create REST API for all agent operations

- Implement agent dashboard UI

## Deliverables

- Agent CRUD API endpoints with validation

- Agent creation wizard UI (4-step flow)

- Container lifecycle manager with graceful shutdown

- Health check probe system (HTTP, TCP, exec)

- Agent dashboard with status cards and quick actions

- Agent detail view with configuration display

## Acceptance Criteria

- Agents can be created from templates in < 30 seconds

- Agents gracefully shut down preserving state

- Health checks detect failures and restart agents within 60 seconds

- Dashboard shows all agents with real-time status

- REST API passes all integration tests

Risks Container startup time may exceed 30-second target ¦ Health check frequency vs. performance trade-off

Week 5-6: Communication & Monitoring MCP Relay, Redis Pub/Sub, Metrics Dashboard

## Goals

- Build MCP protocol relay server for tool sharing

- Implement Redis pub/sub for agent messaging

- Create real-time metrics collection (CPU, memory, network)

- Build metrics dashboard with live charts

- Implement centralized log aggregation

- Build health status overview board

## Deliverables

- MCP relay server with tool discovery and routing

- Redis pub/sub message broker with channel management

- Metrics collector sidecar for each agent container

- Real-time dashboard with Chart.js/Recharts graphs

- Log aggregation service with search and filtering

- Health status board with drill-down capability

## Acceptance Criteria

- Agents can discover and use tools from other agents via MCP

- Messages delivered between agents in < 100ms via Redis

- Metrics displayed with < 5 second latency

- Logs searchable across all agents with < 2 second response

- Health board accurately reflects agent states

Risks MCP relay may introduce latency in tool calls ¦ Redis memory usage may grow unbounded without TTL policies

Week 7-8: Security & Polish RBAC, Audit Logs, UI Polish, Documentation

## Goals

- Implement 4-tier RBAC (Admin, Operator, Developer, Viewer)

- Build encrypted secrets management system

- Create comprehensive audit logging

- Implement tool authorization (allow-lists per agent)

- Polish UI: responsive design, error handling, loading states

- Write user documentation and API docs

## Deliverables

- RBAC middleware with permission checks on all endpoints

- Secrets vault with AES-256 encryption at rest

- Audit log table with tamper detection

- Tool authorization engine with allow/deny lists

- Polished UI with consistent error handling

- User guide, API reference, deployment guide

## Acceptance Criteria

- Each role can only access permitted endpoints

- Secrets encrypted at rest and in transit, never in logs

- All admin actions logged with user, action, timestamp, IP

- Tool access denied unless explicitly allowed for agent

- UI handles all error states gracefully

- Documentation covers all MVP features

Risks RBAC complexity may delay other polish tasks ¦ Documentation scope may exceed available time

# Tech Stack Decisions

Each technology choice is justified by specific requirements of the Hive platform:

| Technology | Choice | Rationale | Alternatives Considered |
| --- | --- | --- | --- |
| Frontend | Next.js 15 + React 19 | Server components for performance, App Router for modern patterns, built-in API routes | Nuxt, SvelteKit, Remix |
| Styling | Tailwind CSS + shadcn/ui | Utility-first CSS for rapid development, shadcn for accessible component primitives | Material UI, Ant Design, Chakra |
| Language | TypeScript 5.x | Type safety catches bugs early, excellent IDE support, same language front and back | Python, Go, Rust |
| Database | PostgreSQL 16 | Battle-tested reliability, JSON support, excellent TypeScript tooling via Drizzle | MySQL, MongoDB, SQLite |
| ORM | Drizzle ORM | Type-safe queries, lightweight, excellent migration system, SQL-like API | Prisma, TypeORM, Sequelize |
| Auth | JWT + bcrypt | Stateless auth for API, refresh tokens for security, bcrypt for password hashing | NextAuth, Clerk, Auth0 |
| Container Runtime | Docker + Podman | Docker for ease, Podman for rootless security, Firecracker for MicroVM isolation | containerd, CRI-O |
| Message Broker | Redis 7 | Pub/sub + caching + sessions in one service, excellent performance | RabbitMQ, NATS, Kafka |
| Reverse Proxy | Traefik v3 | Auto-discovery, Docker integration, automatic TLS, modern configuration | Nginx, Caddy, HAProxy |
| DNS | CoreDNS | Kubernetes-native, plugin architecture, easy custom zones | BIND, dnsmasq, PowerDNS |
| Monitoring | Custom + Prometheus | Custom for MVP speed, Prometheus-compatible for future export | Grafana stack, Datadog |
| AI Integration | Vercel AI SDK | Unified API across providers, streaming support, React hooks | LangChain, custom |

# Development Environment Setup

Prerequisites and setup steps for the development environment:

# Prerequisites Node.js >= 20.x (LTS) pnpm >= 9.x Docker Desktop >= 4.x or Podman >= 4.x PostgreSQL >= 16.x Redis >= 7.x Git >= 2.40 # Clone and setup git clone https://github.com/hive-platform/hive.git cd hive pnpm install cp .env.example .env.local # Database setup pnpm db:generate # Generate migration files pnpm db:migrate # Run migrations pnpm db:seed # Seed with test data # Start development pnpm dev # Next.js dev server (port 3000) pnpm dev:relay # MCP relay server (port 3001) pnpm dev:metrics # Metrics collector (port 3002)

# Testing Strategy

Three-tier testing approach ensuring quality at every level:

| Level | Tools | Coverage Target | Scope |
| --- | --- | --- | --- |
| Unit Tests | Vitest + Testing Library | 80% | Business logic, utilities, React components, API handlers |
| Integration Tests | Vitest + Testcontainers | 60% | API endpoints, database queries, Docker operations, Redis pub/sub |
| E2E Tests | Playwright | Critical paths | Auth flow, agent creation, dashboard interactions, MCP communication |

Testing Philosophy Test the behavior, not the implementation. Every P0 feature must have at least one integration test covering the happy path and one test covering the primary error case. E2E tests cover the 5 most critical user journeys.

# QA Checklist

Quality assurance checklist applied before each sprint completion:

- All P0 acceptance criteria verified manually

- Unit test coverage ≥ 80% for new code

- Integration tests pass against real Docker daemon

- No critical or high-severity security vulnerabilities (npm audit)

- API response times < 200ms for all CRUD operations

- UI renders correctly on Chrome, Firefox, Safari

- No console errors in production build

- Database migrations are reversible

- All API endpoints have input validation

- Error messages are user-friendly (no stack traces in production)

# Definition of Done

A feature is considered 'Done' when all of the following criteria are met:

- Code is written, reviewed, and merged to main branch

- Unit tests written and passing with ≥ 80% coverage

- Integration test covers the happy path

- API documentation updated (OpenAPI spec)

- UI component has loading, error, and empty states

- Accessibility: keyboard navigable, screen reader compatible

- Performance: API response < 200ms, UI render < 100ms

- Security: input validation, auth check, audit log entry

- No TypeScript errors or ESLint warnings

- Deployed to staging environment and manually verified

# Risk Register

Identified risks with probability, impact, and mitigation strategies:

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Docker SDK breaking changes across versions | Medium | High | Pin Docker SDK version, maintain compatibility layer, test on multiple versions |
| Founder 2 availability drops below 20 hrs/week | Medium | High | Cross-train Founder 1 on infra, prioritize security features, document all decisions |
| MCP protocol specification changes | Low | High | Abstract MCP integration behind interface, monitor spec repo, maintain compatibility layer |
| PostgreSQL performance under concurrent agent load | Low | Medium | Connection pooling (pgBouncer), query optimization, read replicas if needed |
| Redis memory exhaustion from pub/sub history | Medium | Medium | Set TTL on all keys, implement message retention limits, monitor memory usage |
| Container startup time exceeds 30-second target | Medium | Medium | Pre-pull base images, optimize Dockerfile layers, implement container pool |
| Scope creep from user feedback during development | High | Medium | Strict feature freeze after Week 2, document all feedback for Phase 2 backlog |
| Security vulnerability discovered in dependencies | Medium | High | Daily npm audit, Dependabot alerts, security review before each sprint |

# Success Criteria

The MVP is considered successful when the following quantified criteria are met:

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Agent creation time | < 30 seconds | Timed from wizard start to agent running |
| Agent startup time | < 10 seconds | Timed from start command to healthy status |
| API response time | < 200ms (p95) | Measured via API latency monitoring |
| Dashboard load time | < 2 seconds | Lighthouse performance score ≥ 90 |
| Concurrent agents | ≥ 50 on single host | Load test with resource monitoring |
| MCP tool call latency | < 500ms relay overhead | Measured via tracing |
| System uptime | 99.5% during testing | Uptime monitoring during beta |
| Test coverage | ≥ 80% unit, ≥ 60% integration | Coverage reports from Vitest |

# Post-MVP Priorities

Features and improvements planned immediately after MVP launch, informed by the P1 feature backlog:

- A2A Protocol Bridge (CM-03) — Enable Google A2A standard communication between agents

- Agent Templates Library (AL-06) — Pre-built templates for common agent patterns

- Advanced Alerting (MN-03) — Configurable alerts with email, Slack, and webhook notifications

- Network Isolation (NW-03) — Per-project network segmentation for security

- Model Routing (MM-02) — Intelligent routing to optimal models based on task type

- Prompt Injection Detection (SC-07) — Real-time detection and prevention

- TypeScript SDK (AC-05) — Official typed SDK for developer integration

- Webhook Integration (CM-04) — Outbound webhooks for external system integration

# Budget Breakdown

Annual infrastructure costs for the MVP deployment:

| Service | Monthly | Annual | Notes |
| --- | --- | --- | --- |
| Hetzner Dedicated Server (AX102) | €130 | €1,560 | AMD Ryzen 9 7950X, 128GB RAM, 2x2TB NVMe |
| Domain & DNS | €2 | €24 | hive.dev or similar |
| TLS Certificates | €0 | €0 | Let's Encrypt (free) |
| Email Service (Resend) | €0 | €0 | Free tier (3,000 emails/month) |
| Monitoring (Uptime) | €7 | €84 | Better Uptime or similar |
| Backup Storage | €5 | €60 | Hetzner Storage Box 1TB |
| GitHub Team | €4 | €48 | 2 seats at $4/month |
| CI/CD (GitHub Actions) | €0 | €0 | Free tier (2,000 min/month) |
| Container Registry | €0 | €0 | GitHub Container Registry (free) |
| Total | €148 | €1,776 | Well under €3,520 budget |

Budget Note The €3,520/year budget provides substantial headroom. Actual costs of ~€1,776/year leave room for GPU instances (€50-100/month) when needed for local model hosting, and unexpected scaling needs. No VC funding required for MVP.

This document is confidential and intended for internal use only. Version 2.0 - Enriched Edition.